## ProjectInitiation
Project Breakdown: Automating YouTube Feed Training
🎯 Objective:
Train YouTube’s recommendation engine to prioritize Power BI content by automating searches, video interactions, and playlist management.
🛠️ Key Components
1. YouTube Data API Integration
Fetch latest Power BI-related videos programmatically.
Extract video titles, URLs, descriptions.
2. Automated Video Interaction (Algorithm Training)
Watch videos programmatically (Python + Selenium).
Engage via likes, comments, and watch time to influence recommendations.
3. Playlist Automation
Create & update a Power BI learning playlist dynamically.
Automate adding new relevant videos to the playlist.
4. Scheduled Daily Execution
Automate searches & interactions daily using Python scripts.
Ensure continuous training of YouTube’s algorithm.
📌 Deliverables
✅ A Python script to fetch and display relevant Power BI videos.
✅ Automated YouTube interactions (watching, liking, playlist curation).
✅ Optimized YouTube feed for Power BI learning over time.
⏳ Timeline
1. Day 1-3 – Set up YouTube API, fetch & parse results.
2. Day 4-6 – Implement video watching automation.
3. Day 7-9 – Automate playlist curation.
4. Day 10-14 – Fine-tune recommendations, schedule script execution.
Would you like a cron job setup for daily execution? 🚀